## EX - Sprint Planning Template
|  | PROJECT MANAGER |  | START DATE | END DATE | OVERALL PROGRESS | PROJECT DELIVERABLE
|  |  |  | 2028-02-22 | 2028-06-18 | 35% | SCOPE STATEMENT
TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START DATE | END DATE | DURATION in days | STATUS | PRIORITY | COMMENTS
SPRINT A |  | Patricia Teixeira |  | 2028-02-22 | 2028-04-16 | 55
G002 | As Project Manager, I want the team to elaborate a Domain Model using DDD. | Patricia Teixeira |  | 2028-03-22 | 2028-04-16 | 26 | Needs Review | High
G003 | As Project Manager, I want the team to use the defined project repository and continuous integration server. | Mariana Rocha | 5 | 2028-03-24 | 2028-03-30 | 7 | Complete | Medium
G004 | As Project Manager, I want the team to add to the project the necessary scripts, so that build/executions/deployments/... can be executed effortlessly. | Duarte Fonseca |  | 2028-03-25 | 2028-03-31 | 7 | Complete
G005 | As Project Manager, I want the team to configure the project structure to facilitate / accelerate the development of upcoming user stories. | Miguel Cardoso |  | 2028-03-24 | 2028-03-30 | 7 | Complete
G006 | As a Project Managers, I want the system to support and apply authentication and authorization for all its users and functionalities. | Miguel Seixas |  | 2028-03-24 | 2028-03-30 | 7 | Complete
SPRINT B |  | Miguel Cardoso |  | 2028-04-17 | 2028-05-21 | 35
1001 | As Manager, I want to be able to register, disable/enable, and list users of the system (Teachers and Students, as well as Managers) | Mariana Rocha |  | 2023-05-01 | 2028-04-30 | 1827 | Complete | High | 1
1002 | As Manager, I want to create courses | Miguel Cardoso |  | 2028-05-10 | 2028-05-18 | 9 | Complete | High | 1
1003 | As Manager, I want to open and close enrollments in courses | Miguel Seixas |  | 2028-05-11 | 2028-05-19 |  | Complete | High | 1
1004 | As Manager, I want to open and close courses | Duarte Fonseca | 5 | 2028-05-10 | 2028-05-18 | 9 | Complete | Medium | 1
1005 | As Manager, I want to set the teachers of a course | Mariana Rocha |  | 2028-04-17 | 2028-04-30 | 14 | In Progress | High | 1
1006 | As User, I want to list all the courses that are available to me | Miguel Cardoso |  | 2028-04-17 | 2028-04-30 | 14 | Complete | High | 1
1007 | As Manager, I want to enroll students in bulk by importing their data using a csv file | Duarte Fonseca | 3 | 2028-05-18 | 2028-05-21 | 4 | Complete | Low | 5
1008 | As Student, I want to request my enrollment in a course | Miguel Seixas |  | 2028-04-17 | 2028-04-30 | 14 | In Progress | High | 1
1009 | As Manager, I want to approve or reject students applications to courses | Patricia Teixeira |  | 2028-04-17 | 2028-04-30 | 14 | In Progress | High | 1
1010 | As Teacher, I want to schedule a class | Miguel Seixas |  | 2028-04-17 | 2028-04-30 | 14 | Needs Review | High | 1
1011 | As Teacher, I want to schedule an extraordinary class | Mariana Rocha |  | 2028-04-17 | 2028-04-30 | 14 | On Hold | Low | 5
1012 | As Teacher, I want to update the schedule of a class | Miguel cardoso |  | 2028-04-17 | 2028-04-30 | 14 | Complete | Low | 5
2001 | As Teacher, I want to create an exam | Patricia Teixeira |  | 2028-04-17 | 2028-04-30 | 14 | Complete | High | 1
2002 | As Student, I want to view a list of my future exams | Miguel Seixas |  | 2028-04-17 | 2028-04-30 | 14 | Needs Review | High | 5
2003 | As Teacher, I want to view a list of all exams in a course | Mariana Rocha |  | 2028-04-17 | 2028-04-30 | 14 | Complete | High | 5
2007 | As Teacher I want to add/update exam questions to a repository of exam questions to be used in automatic formative exams | Patricia Teixeira |  | 2028-04-18 | 2028-05-01 |  | Complete | High | 1
2008 | As Teacher, I want to create/update automatic formative exams | Miguel Cardoso |  | 2028-04-19 | 2028-05-02 |  | In Progress | High | 1
3001 | As Project Manager, I want the team to prepare the communication infrastruture for the Shared Boards and the depoyment of the solution | Miguel Cardoso |  | 2028-04-17 | 2028-04-30 | 14 | On Hold | High | 1
3002 | As User, I want to create a board | Duarte Fonseca | 8 | 2028-04-20 | 2028-05-10 | 21 | Complete | High | 1
3003 | As Project Manager, I want the team to "explore" the synchronization problems related to the shyncronization of shared boards and design a conceptual solution based on practical evidence. | Patricia Teixeira |  | 2028-04-17 | 2028-04-30 | 14 |  | High | 1
4001 | As User, I want to schedule a meeting | Patricia Teixeira |  | 2028-04-17 | 2028-04-30 |  | Complete | Low | 5
5001 | As software product client, I want the team (software product supplier) to prepare a presentation focusing on the following aspects: (i) main objectives of the system; (ii) adopted development process and planning; (iii) teamwork methodology and conflict resolution strategy; (iv) product quality; (v) expected results; (vi) 'turnkey' format for software delivery/sale; among others relevant aspects. | Duarte Fonseca | 1 | 2028-05-18 | 2028-05-21 | 4 | Complete | Low
SPRINT C |  |  |  | 2028-05-22 | 2028-06-18 | 28 | On Hold

## BLANK - Sprint Planning
SPRINT PLANNING TEMPLATE
PROJECT NAME |  |  | PROJECT MANAGER |  | START DATE | END DATE | OVERALL PROGRESS | PROJECT DELIVERABLE
[7 empty] | 0% | SCOPE STATEMENT
At Risk? | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START DATE | END DATE | DURATION in days | STATUS | PRIORITY | COMMENTS
SPRINT 1
Feature 1
Feature 2
Feature 3
SPRINT 2
Feature 1
Feature 2
Feature 3
SPRINT 3
Feature 1
Feature 2
Feature 3
SPRINT 4
Feature 1
Feature 2
Feature 3
SPRINT 5
Feature 1
Feature 2
Feature 3
Right-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
YES / NO | PRIORITY | STATUS
Yes | Low | Not Started
No | Medium | In Progress
| High | Complete
Needs Review
Approved
Overdue
On Hold

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.